## Sheet1
S.No. | API Issues | Created ON | Priority | Status | Occurences | JIRA link
| [Query editor]: When we give NLP from the 2nd line then open AI API’s are not calling. https://www.screencast.com/t/tU0U9DXGm : DAPP-1243 | 2023-03-17 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1243
| [Contract Utility>Eatherium]:On Fire Fox while aproving request it shows forbidden error. https://www.screencast.com/t/pAko0gzm26S DAPP 1317 | 2023-03-27 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1317
| [Admin > Ploygon]: Getting internal server error while approving request of polygon https://www.screencast.com/t/KnQBaGKGe DAPP 1318 | 2023-03-27 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1318
| [ChatGPT]: ' --get top 10 data from BLOCK table' gives me network error with -- and without -- worked well. https://www.screencast.com/t/W4qdpuUju7wS: DAPP-1169 | 2023-03-09 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1169
| [My Queries]: When we sort via Tags then it shows me error message: Unable To Complete Requested Operation Due To Technical Issue. https://www.screencast.com/t/SodPcRooR04z : DAPP-1278 | 2023-03-22 | Medium |  |  | https://space-and-time.atlassian.net/browse/DAPP-1278
| [ChatGPT]: When I give NLP 'Select top 10 transaction from SUI model' it shows me error 'No cluster mapped' but it worked for 'Get top 10 transaction from SUI model ' : https://www.screencast.com/t/5QpuHtAzFpi : DAPP-1247 | 2023-03-20 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1247
| [Dashboard]: Chart is not pinned to the dashboard and shows an error message. https://www.screencast.com/t/IS4KkP3YQHF DAPP 1297 | 2023-03-23 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1297
| [Queries] : Filter for Published, Draft and Completed not working in My Queries | 2023-03-23 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1299
| [Insights]: In chrome Browser when we select third community for last 30 days and date is 29 April then declustred network graph are stick to each other. | 2023-03-16 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1224
| [Query editor]: Open AI query editor is very slow to convert the NLP in SQL and running the query. https://www.screencast.com/t/dEJKw0qtWRN: DAPP-1172 | 2023-03-09 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1172
| [Chart Suggestions]: Counter icon is not clickable which shows under ‘Query Visualization’ section. https://www.screencast.com/t/dvpTQ8dV5Bj : DAPP-1272 | 2023-03-21 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1272
| [Queries]: In explore, queries are not searched from popular tags. | 2023-03-20 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1248
| [Query> Charts > Data sets > Counter]: Search not working from popular tags. | 2023-03-21 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1266
| [Charts]: Charts are taking time to load. https://www.screencast.com/t/tUP5DPD3 | 2023-03-23 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1287
| [Contract Utility]: When demo mode is ON then namespace is not visible in data sets screen. https://www.screencast.com/t/LJym1TzPaF DAPP 1268 | 2023-03-21 | High |  |  | https://space-and-time.atlassian.net/browse/DAPP-1268
| [Contract Utility]: After Sending a request it shows an error in the contract utility https://www.screencast.com/t/cMt9vv6cX DAPP 1291 | 2023-03-23 |  | Fixed |  | https://space-and-time.atlassian.net/browse/DAPP-1291
| [Query Editor]: On running the query the error message shows 'Fail to generate graph' https://www.screencast.com/t/A8eogF1VgoMT DAPP 1209. | 2023-03-14 |  | Fixed |  | https://space-and-time.atlassian.net/browse/DAPP-1209
| [Query Editor]: when I run query with CTRL + ENTER then it shows error message 'No cluster mapped for Resource PUBLIC:TRANSACTION' but i am run NLP as a run query button then it shows sql https://www.screencast.com/t/HQ9nn1rSYep DAPP 1182. | 2023-03-10 |  | Fixed |  | https://space-and-time.atlassian.net/browse/DAPP-1182
| [Contract Utility]: [Contract Utility]: While sending a request for table creation, it shows an error message. https://www.screencast.com/t/BlFjiqtrxh0 DAPP 1170 | 2023-03-09 |  | Fixed |  | https://space-and-time.atlassian.net/browse/DAPP-1170
| [Contract Utility]: When we index tables under a predefined namespace like ‘Ethereum’ then on Datasets screen it shows under ‘Core’ table group. https://www.screencast.com/t/6oAj7iFCyj : DAPP-1234 | 2023-03-16 |  | Fixed |  | https://space-and-time.atlassian.net/browse/DAPP-1234
| [Query Editor]: Error while saving query from 'Please Configure Visualization' for untitled queries. https://www.screencast.com/t/JkVxi17i : DAPP-1270 | 2023-03-21 |  | Fixed |  | https://space-and-time.atlassian.net/browse/DAPP-1270